## Sheet1
S. No | Action items | Owners | Deadline | Status
1 | Extend the project scope to the team of 5 | Vikas, Sai Krishna, Revanth, Siri, Sai Teja | 2018-09-06 | Closed
2 | Complete team deliverable 1 documents | Vikas, Sai Krishna, Revanth, Siri, Sai Teja | 2018-09-12 | Open
3 | Push the initial structure of Andriod Project | Sai krishna | 2018-09-18 | Open
4 | Need to have team discussion on suggestions | Vikas | 2018-09-25 | Closed
5 | Need to include project scope for Changing ringer volume and Enhanced activity logs | Vikas, Sai Krishna | 2018-10-03 | Open